CONSOLIDATED CARPET INDUSTRIES LIMITED CCIL ¦ New Delhi ERP & CRM TRANSFORMATION PROJECT BRIEFING DOCUMENT Microsoft Dynamics 365 Business Central + MiClient CRM Prepared by: Anirudh Under supervision of: Dr. Pal Date: March 4, 2026

# 1.  Overview & Context

Consolidated Carpet Industries Limited (CCIL), headquartered in New Delhi, is undertaking a comprehensive digital transformation initiative involving two parallel technology projects:

| Project | Details |
| --- | --- |
| ERP Implementation | Microsoft Dynamics 365 Business Central — replacing legacy Dynamics NAV. Vendor: Transform Infotech (Mumbai). Contract: ₹15,00,000 fixed. |
| CRM Implementation | MiClient CRM — AI-enabled sales automation with ERP integration. Vendor: MiClient Private Limited (Gurgaon). Contract: ₹7,32,000 + GST. |

# 2.  Key Stakeholders

| Name | Organization | Contact |
| --- | --- | --- |
| Ashish Garg | CCIL | ashish@ccil.in |
| Dhruv Sodhani | CCIL | dhruv@ccil.in |
| Anil Mehta | CCIL | anil@ccil.in |
| Shekhar Nadkar | Transform Infotech | shekhar@transform.org.in |
| Pratiksha U | Transform Infotech | pratiksha@transform.org.in |
| Chandan K. Ghosh | MiClient | chandan@miclient.ai |
| Navneet Choudhary | MiClient | navneet@miclient.ai |
| Dr. Pal | External Consultant | — |
| Anirudh | Dr. Pal's Team | — |

# 3.  Project 1 — Microsoft Dynamics 365 Business Central (ERP)

## 3.1  Vendor & Commercials

| Parameter | Details |
| --- | --- |
| Vendor | Transform Infotech, Mumbai — Shekhar Nadkar (Proprietor) |
| Contract Value | ₹15,00,000 — Fixed, Lump Sum, All-Inclusive |
| Travel Expenses | Reimbursable up to ₹75,000 (with prior written approval) |
| Post Go-Live Support | ₹1,250/hour (on written approval only) |
| Penalty for Delay | 0.5% per week beyond April 1, 2026 — capped at 5% of contract |
| Retention | 5% withheld per RA bill — released after 1-year defect liability period |

## 3.2  Scope of Work

The ERP implementation covers the following functional areas:

- Financial Accounting & Statutory Reporting, Budgeting, Forecasting & MIS

- Fixed Asset Management with automated cut-off determination

- Procurement — Domestic & Imports (with bonded warehouse, duty tracking, forex)

- Inventory & Warehousing — multi-location, bin-level with barcode integration

- Sales & Distribution — Domestic & Export

- GST and statutory compliance, E-Way Bill & E-Invoice integration

- Receivables & Payables automation with aging and reminder workflows

- Banking — LC, BG, cash management, automated daily reconciliation

- AI-assisted dashboards and inventory cut-off logic

- CRM Integration via APIs — ERP is the authoritative master database

- Logistics integrations — transporters, freight forwarders, shipment tracking

- Data migration from legacy NAV — cleansing, standardization, reconciliation

- Testing (Functional, Integration, UAT), Training & Go-Live support

## 3.3  Milestone Schedule & Payment Terms

| # | Milestone | Deadline | Payment % | Status |
| --- | --- | --- | --- | --- |
| M1 | Assessment & Planning | 24 Jan 2026 | 20% | DONE |
| M2 | Solution Design & Environment Setup | 3 Feb 2026 | 5% | DONE |
| M3 | Core Configuration & Extension Development | 23 Feb 2026 | 5% | DONE |
| M4 | Data Migration — Trial Loads | 10 Mar 2026 | 10% | Partially done |
| M5 | Integration & System Testing | 20 Mar 2026 | 20% | PENDING |
| M6 | UAT, Training & Cut-over Preparations | 15 Mar 2026 | 20% | PENDING |
| M7 | GO-LIVE & Stabilization | 01 Apr 2026 ★ | 10% | HARD DATE |
| M8 | Phase II — Post Go-Live Requirements | 15 Jun 2026 | 10% | FUTURE |

# 4.  Project 2 — MI Client CRM

## 4.1  Vendor & Commercials

| Parameter | Details |
| --- | --- |
| Vendor | MiClient Private Limited, Gurgaon |
| Implementation Cost | ₹1,82,000 (one-time, incl. configuration, training, go-live) |
| Annual Subscription | ₹5,50,000 (50 users @ ₹11,000 each) — exclusive of GST |
| Total Contract Value | ₹7,32,000 + GST (18%) = ₹8,63,760 total |
| Advance Paid (40%) | ₹3,45,740 (PI #FY 25-26/0202 — Nov 7, 2025) |
| Penalty for Delay | 0.5% per week — max 5% of milestone value |

## 4.2  CRM Features & Scope

- OCR-based automated data capture — visiting cards, emails, POs, WOs

- Sales Quotation & Proforma Invoice generation with WhatsApp/email delivery

- Special rate approval mechanism — CPQ (Configure, Price, Quote) with live margin analysis

- Chatbot-based stock reservation with ERP real-time availability check

- AI-based MIS dashboards — invoiced amounts, orders in hand, sales team performance

- Image-based product matching and AI product recommendation on search

- Automated shipment & order status tracking via ERP APIs

- Lead-to-order conversion tracking and sales performance reports

- Marketing automation — campaigns based on historical CRM & ERP data

- Milestone-based receivable reminders — automated pop-ups and emailers

- Daily sales activity tracking per sales person

## 4.3  Original Project Timeline (Already Delayed)

| # | Activity | Original Deadline | Status |
| --- | --- | --- | --- |
| 1 | Company signup, user setup, client & product data upload | 2nd–3rd week of Nov 2025 | Done |
| 2 | Quotation template setup, T&C, bank details, training | 4th week of Nov 2025 | Done |
| 3 | Phase 1 Go-Live — CRM/CPQ & Sales Automation | 4th week of Nov 2025 | Done |
| 4 | ERP Integration (BC 365 APIs), OCR, AI features | 4th week of Dec 2025 | OVERDUE |
| 5 | Reporting, Reconciliation, Marketing Automation | 4th week of Dec 2025 | OVERDUE |
| 6 | Phase 2 Go-Live — Full ERP Integration | 1st week of Jan 2026 | OVERDUE |

# 5.  Integration Architecture — ERP & CRM

The two systems are designed to work as a unified platform with clearly defined roles:

| Microsoft Dynamics 365 BC (ERP) | MiClient CRM |
| --- | --- |
| Master/Backend — Single Source of Truth | Frontend — Used by Sales Team daily |
| Holds all financial, inventory, order data | Reads/writes to ERP via secure APIs |
| Transform Infotech builds ERP-side APIs | MiClient builds CRM-side API connectors |
| Governs stock availability, pricing, invoicing | Governs lead capture, quotes, reservation requests |

## 5.1  Key Integration Data Flows

- Customer, Vendor & Item Master synchronization — ERP to CRM

- Quotation, PI, Sales Order & Work Order exchange — CRM to ERP

- Real-time stock availability, reservation, block/unblock — bidirectional

- Indent creation and PO generation triggers — CRM initiates, ERP confirms

- Shipment, invoicing, receivables & payment status updates — ERP to CRM

- Financial and MIS data exposure to CRM dashboards — ERP to CRM

⚠ Integration Risk: ERP and CRM are being built by two different vendors. API contracts between Transform Infotech and MiClient may not be aligned. This is the most critical gap to identify

# 6.  AI Integration Points

The following AI capabilities are planned across both platforms. These are core to Dr. Pal's engagement mandate:

## 6.1  AI Features in MiClient CRM

| AI Feature | Description |
| --- | --- |
| OCR Data Capture | Visiting cards, email orders, POs, WOs — auto-extracted via AI/OCR |
| AI MIS Dashboards | Auto-generated sales synopsis, charts, and suggestions for management |
| Image-Based Product Matching | Upload product image to find matching SKUs in catalog |
| AI Product Recommendation | Suggests relevant products based on client specs and history |
| Lead-to-Order Analytics | AI reports on conversion rates, quotation frequency, team performance |
| Chatbot — Stock Reservation | Chatbot interface for real-time stock queries and reservation requests |
| Order AI Parsing | AI reads incoming orders (PDF/Word/email/WhatsApp) and maps to CRM PI/Quotation |

## 6.2  AI Features in BC 365 ERP

| AI Feature | Description |
| --- | --- |
| Inventory Cut-off Logic | AI-assisted reorder suggestions based on historical and recent sales data |
| AI-Assisted Dashboards | Real-time management dashboards with intelligent KPIs and alerts |
| Automated Reconciliations | Customer and vendor reconciliation with AI-generated synopsis |
| Slow/Dead Stock Detection | Periodic AI pop-ups identifying slow-moving and dead stock with actions |
| Automated Emailers | Receivable due-date reminders, daily bank balances to management |
| Commission Sheet Automation | Auto-generated commission based on receivables, project costing & WO mapping |

# 7.  Key Questions for Tomorrow's Meetings

## 7.1  For MiClient (CRM Meeting)

- Have the ERP integration APIs been defined and documented? What is the current API status?

- Is MiClient coordinating directly with Transform Infotech on API contracts?

## 7.2  For Transform Infotech / BC 365 Consultant (ERP Meeting)

- Have the CRM integration APIs been designed and shared with MiClient?

## 7.3  For AI Integration (Both Meetings) DONE

- Which AI capabilities within MiClient are standard (built-in) vs. to be custom-developed?

- What AI features does BC 365 support natively (Copilot, Power BI AI insights)?

- Is there a defined API schema/contract between CRM and ERP for AI data flows?

- Who is responsible for testing AI features — Transform, MiClient, or CCIL?

This document is confidential and prepared for internal use by CCIL and Dr. Pal's team only. Prepared by Anirudh ¦ March 4, 2026 ¦ Under supervision of Dr. Pal