## Sheet1
S.No | Task/Activity | Description | Responsible Party | End Date
Phase 1- CRM/CPQ Module - Initial Setup
1 | Company SignUP | set up the Company Account | CCIL/MiCLIENT | 2nd week of Nov
1 | Provide User Details | Collect user details (Name, Phone Number, Email ID) | CCIL | 2nd week of Nov
2 | Add Users to Portal | Add user to the portal and create logins for user | CCIL/MiCLIENT | 2nd week of Nov
3 | Provide Client Data | Provide client data for upload | CCIL | 2nd week of Nov
4 | Add Client Data to System | Add client data to the system | MiCLIENT | 3rd week of Nov
5 | Provide Product Data | Provide product data for upload | CCIL | 3rd week of Nov
6 | Add Product Data to System | Add product data to the system | MiCLIENT | 3rd week of Nov
7 | Set Up Quotation and invoice Template | Set up the template for quotations and invoice | MiCLIENT | 3rd week of Nov
8 | Signoff for Template | Get client signoff on the quotation template | CCIL/MiCLIENT | 3rd week of Nov
9 | Include Terms and Conditions | Include terms and conditions in quotations and invoices | CCIL/MiCLIENT | 3rd week of Nov
10 | Add Bank Account Details | Add bank account details for quotations and invoices | CCIL | 4th week of Nov
12 | Initial Briefing | Provide an initial briefing session | MiCLIENT | 4th week of Nov
14 | Conduct User Training | Conduct user training on the CRM | CCIL/MiCLIENT | 4th week of Nov
15 | Dashboard, CRM, Deals and PI | Training is done with you and your user | MiCLIENT | 4th week of Nov
Phase 2- Microsoft Navision BC 365 ERP integration/Report
16 | Microsoft Navision BC 365 ERP | Microsoft Navision BC 365 ERP integration through API | CCIL/MiCLIENT | 3rd week of Dec
17 | Automated capture | Automated data capture through OCR and AI from visiting cards, emails, orders, POs, and WOs. | MiCLIENT | 3rd week of Dec
18 | Sales flows | Quotation & PI creation in CRM with real-time push/pull to/from BC 365. | CCIL/MiCLIENT | 3rd week of Dec
19 | Stock/Order reservation: | Reservation APIs, indent creation, and chatbot interface for users. | MiCLIENT | 3rd week of Dec
20 | AI features | MIS dashboards, automated tracking of shipments, through ERP APIs and milestone-wise receivable reminders. | CCIL/MiCLIENT | 4th week of Dec
21 | Image matching | Upload/carousel-based image similarity to find matching products in catalog. | MiCLIENT | 4th week of Dec
22 | Reporting & Reconciliation | Live financials, reconciliation reports, KPIs, charts. | MiCLIENT | 4th week of Dec
23 | Marketing automation | Campaigns and promotions based on historical behavior and CRM/ERP data. | MiCLIENT | 4th week of Dec
24 | Report | AI-based reports to track lead-to-order conversion, quotation frequency, and sales team performance to help improve overall sales efficiency; being insights to help management monitor efficiency, improve conversion rates, and optimize sales strategies across regions and teams | MiCLIENT | 4th week of Dec
| Go-Live with Phase 1 | Go live with Phase 1 CRM/CPQ and Sales automaton implementation | CCIL | 4th week of Nov
| Go-Live with Phase 2 | Go live with Phase 2 Microsoft Navision BC 365 ERP integration/Reports | CCIL | 1st week of Jan