What You MUST Know Before Helping Integrate CRM & ERP

1. 🔵 Current State of Both Systems

MiClient CRM — Phase 1 is DONE:

- Web application is live

- Users are set up, client data uploaded, product data loaded

- Quotation and PI templates are configured

- Sales team can already create quotes and PIs manually

- Phase 2 (ERP integration) has NOT started — was due Dec 2025, still pending

BC 365 ERP — Mid-Migration:

- M1, M2, M3 are done (Assessment, Design, Core Config)

- M4 Data Migration is partially done

- M5 (Integration Testing) and M6 (UAT) are still pending

- APIs have NOT been built yet by Transform Infotech

- Go-Live target: April 1, 2026

Bottom line: Right now the two systems are completely isolated — no connection exists between them yet.

2. 🔴 The Golden Rule — Who Owns What

This is the most critical thing to understand before any integration discussion:

|  | MiClient CRM | BC 365 ERP |
| --- | --- | --- |
| Role | Frontend — Sales team uses this | Backend — Master database |
| Owns | Leads, quotes, PI, customer interactions | Stock, pricing, invoices, financials |
| API responsibility | CRM-side connectors (MiClient builds) | ERP-side APIs (Transform Infotech builds) |
| Who is master? | Follower — reads from ERP | Master — source of truth |

If there is ever a data conflict between the two systems, ERP always wins.

3. 🟡 The 8 Integration Flows You Need to Understand

These are the actual data conversations that need to happen between the two systems:

Flow 1 — Master Data (ERP → CRM) ERP pushes customer master, item/product master, pricing, vendor data to CRM so the sales team has accurate data when making quotes.

Flow 2 — Quotation/PI (CRM → ERP) When a salesperson creates a quote in MiClient, it needs to sync to ERP so ERP knows about it.

Flow 3 — Stock Availability (CRM queries ERP) When a salesperson wants to check stock before promising a customer, CRM asks ERP in real time — ERP responds with available quantity per location.

Flow 4 — Stock Reservation (CRM → ERP) When a salesperson reserves stock via chatbot, CRM sends a reservation request to ERP — ERP blocks the quantity and confirms back.

Flow 5 — Sales Order (CRM → ERP) When a customer order is confirmed in CRM, it pushes a Sales Order to ERP for processing, invoicing, and dispatch.

Flow 6 — Indent/PO Creation (CRM triggers ERP) If stock is not available, CRM triggers an indent in ERP to initiate a purchase order for import or domestic procurement.

Flow 7 — Shipment & Delivery Status (ERP → CRM) Once ERP dispatches an order, it pushes shipment tracking, delivery status, and e-way bill info back to CRM so the salesperson can see it.

Flow 8 — Financial Data for MIS (ERP → CRM) ERP pushes invoiced amounts, outstanding receivables, payment status, and collection data to CRM dashboards so management can see real-time sales MIS.

4. 🟠 The API Architecture You Need to Understand

BC 365 exposes data through OData REST APIs — this is Microsoft's standard. MiClient will call these APIs from their side. Here is what this means practically:

- Transform Infotech will create API Pages in BC 365 for each data entity (Items, Customers, Sales Orders, Stock, etc.)

- These API pages expose endpoints like: GET /api/items, POST /api/salesorders, GET /api/stock/{itemNo}

- MiClient will call these endpoints from their CRM application

- Authentication will be via OAuth 2.0 (standard for BC 365 cloud)

- Data format will be JSON

Your job is to make sure both teams are building to the same API contract — same field names, same data formats, same error handling.

5. 🔴 The Biggest Risk You Face

The two vendors have never sat in a room together to agree on the API contract. Transform Infotech is building ERP APIs based on their understanding. MiClient is building CRM connectors based on their understanding. If these don't match, nothing will work when they try to connect — and with April 1 as the deadline, there is no time to fix major mismatches.

Your most important job right now is to get both vendors on the same call and make them agree on a written API contract before any more development happens.

6. ✅ What to Do First — In Order

- Get the API contract meeting done — Transform Infotech + MiClient + you on one call

- Understand what APIs Transform has already built (if any) in BC 365

- Understand what MiClient expects from those APIs (field names, formats, frequencies)

- Document the gaps between what each side expects

- Then build the integration document